HD CONNEX

AI Systems  |  Automation  |  Web Infrastructure

PROJECT SCOPE & DELIVERY OUTLINE

The Colony OK  —  thecolonyok.com

Conservative Media Hub  |  Phase 1 Build

Prepared: May 2026

# Project Overview

The Colony OK is being built into a full-scale conservative media hub — combining independent investigative journalism, podcasting, live programming, and daily news under one digital roof.

HD Connex is responsible for the end-to-end design, development, and automation infrastructure that makes this platform function at launch — and scale cleanly beyond it.

This document outlines exactly what will be built, in what order, and how each component serves the platform's mission.

# What We Are Building

| PLATFORM COMPONENT | PURPOSE |
| --- | --- |
| Homepage | Command center — featured stories, live feed, podcast access, membership CTA |
| Top Stories Section | Article hub for independent investigative journalists to publish content |
| Podcast Directory | Grid of all shows — each linking to a dedicated podcast page |
| Individual Podcast Pages | Per-show page with episodes, host bio, episode player, and subscriber links |
| Live Shows | Embedded live stream integration for broadcasts and live programming |
| Daily News Feed | Regularly updated digest of news content for daily readers |
| $4.99 Membership System | Paywall for full content access — articles, podcasts, live shows |
| Content Submission Pipeline | Automated intake system for journalists to submit articles for publishing |
| Podcast Auto-Update System | RSS-driven automation — new episodes publish to pages without manual work |

# Delivery Phases

| PHASE 1 AUDIT & ARCHITECTURE Days 1–2 |  |
| --- | --- |
| ● | Gain access to thecolonyok.com and audit current site structure and hosting environment |
| ● | Determine what stays, what gets rebuilt, and what platform powers the new build |
| ● | Map full site architecture — all sections, user flows, and content categories |
| ● | Define content submission and publishing workflow before a single line is written |
| ● | Lock the design direction — Jake selects from reference sites and we execute from that point |

| PHASE 2 DESIGN & CORE BUILD Days 3–8 |  |
| --- | --- |
| ● | Homepage: dark, bold media aesthetic — hero section, featured stories, podcast row, news ticker, membership CTA |
| ● | Top Stories section: article feed with thumbnail, headline, author, date, and category filtering |
| ● | Full article pages: formatted, clean reading experience with author byline and related content |
| ● | Podcast directory: show grid with cover art, host name, episode count — all clickable |
| ● | Individual podcast pages: show bio, full episode list with embedded audio player, subscribe links |
| ● | Live Shows section: embedded live stream player (YouTube Live, Rumble, or equivalent) |
| ● | Daily News feed: structured digest format — updated regularly and scannable on load |

| PHASE 3 MEMBERSHIP & MONETIZATION Days 5–9 |  |
| --- | --- |
| ● | Implement $4.99/month membership system with Stripe payment processing |
| ● | Define free vs. gated content — free users see headlines and previews only |
| ● | Member dashboard: full access to all articles, podcast episodes, and live shows |
| ● | Subscription confirmation flow, receipt emails, and self-managed account options |
| ● | Foundation laid for future tiers: annual plan, supporter level, sponsor packages |

| PHASE 4 AUTOMATION SYSTEMS Days 6–10 |  |
| --- | --- |
| ● | Content submission pipeline: journalists submit articles via form — drafts stage automatically for review |
| ● | Approval workflow: Jake receives notification, reviews, and publishes with one click |
| ● | Podcast RSS integration: new episodes from hosting platform publish to show pages automatically |
| ● | No manual re-uploading required — the system updates itself as content is added |
| ● | Contributor account system: each journalist gets a login with their own author profile |

| PHASE 5 QA, SPEED & SEO BASELINE Days 10–14 |  |
| --- | --- |
| ● | Full mobile QA across iOS and Android — every section tested before approval |
| ● | Page speed optimization: image compression, caching, and media load performance |
| ● | SEO structure: meta titles, descriptions, article schema, and podcast schema markup |
| ● | All internal links, buttons, and flows tested end-to-end |
| ● | Journalist accounts onboarded and tested — submission pipeline confirmed working |

| PHASE 6 LAUNCH & ANNOUNCEMENT PREP Days 14–20 |  |
| --- | --- |
| ● | Final review session with Jake — walk through every page and feature before go-live |
| ● | Cason onboarded to podcast system — first shows live and verified |
| ● | At least 5 journalist contributors active with working submission access |
| ● | Platform announcement-ready for campaign window — membership live, content populated |
| ● | Launch checklist completed: domain, SSL, email notifications, backup, and analytics |

# What You Will Have at Launch

| LAUNCH-DAY DELIVERABLES |  |
| --- | --- |
| Live Platform | thecolonyok.com fully rebuilt and operational |
| Top Stories | Article publishing system with journalist submission pipeline |
| Podcast Hub | Show directory + individual podcast pages with auto-updating episodes |
| Live Shows | Embedded live stream integration ready for broadcast |
| Daily News | Structured news digest section live and formatted |
| $4.99 Membership | Stripe-connected paywall — subscriptions processing on day one |
| Automation | Content auto-updates, episode syncing, submission pipeline all active |
| Mobile Ready | Fully responsive across all devices |
| SEO Foundation | Article and podcast schema structured for search indexing |
| Contributor Access | Journalist accounts and podcast host access configured and tested |

# Ongoing Support

The relationship does not end at launch. HD Connex remains available for:

- New podcast page setups as additional shows join the network

- Feature additions as the platform grows — supporter tiers, advertiser pages, video archives

- Monthly performance reporting: subscriber counts, top content, and traffic trends

- Automation updates and content pipeline adjustments as the team and workflow evolve

- Priority response for technical issues — fast-moving media operations require fast support

HD Connex  —  Built to execute.

Questions or adjustments to this scope: connect directly with Heath.