## Summary
THE COLONY OK — SITE AUDIT REPORT SUMMARY
Layer | Key Strength | Key Weakness | Missing/Failure | Priority Improve
UI/UX | Design system tokens + zero radius + N° + hub comments + new components (AuthorityBadge, ClipsTeaser, Paywall) + a11y baseline + E-E-A-T + competitor signals | Inline styles/raw hex (120+), radius violations, touch <44px, A11y gaps, repetition of CTAs, hub leaks, design system drift, motion inconsistent | Functional clips/forum, transcripts integration, advanced personalization, full hub purity, design system enforcement | Purge inlines/raw (priority 1), enforce zero-radius, remove repeats, a11y/touch 44px, image consistency, hub fidelity
Technical | Security headers (HSTS etc.), next/image widespread, SEO metadata + sitemap + JsonLd, ISR/SSG hybrid, motion + reduced-motion, PWA basics + sw push + crons, build clean | External fonts (no next/font), PWA incomplete (no icons dir/SW registration/offline per strategy), raw <img>, inline in system pages, no CSP, Sentry missing, limited realtime client, some perf | Full PWA/TWA (icons, SW full, assetlinks, rural packs), next/font, CSP, Sentry full, realtime client wiring, advanced SEO | PWA/TWA completion, fonts/CSP/Sentry, image consistency, SEO advanced, realtime client, perf (fonts/inline/dupe motion)
Content/IA | Hub model (curated teasers + N° + explicit comments), dedicated immersive (Live TV HUB + guide + clips, podcasts deep + per-ep + chapters, journalists authority + badges, contributors tiers + work rails + E-E-A-T, stories immersion + Paywall, pricing/about pure), implemented ideas (clips teasers, badges, E-E-A-T, live polish) | Repetition of membership/masthead CTAs/grids on home + journalists leak + vs, clips/community surface-only (teasers only, no functional upload/forum per RICH), data/content thin vs ambition (generic shows, fallbacks, partial transcripts/search), hub leaks (full grids on home), dev pollution | Full clips DB/UI + forum (upload, moderation, embeds, threaded per RICH), transcripts + AI pipeline full, advanced personalization, journalist portfolios full + separation, local rural content depth (per LOCAL), clips in search + VideoObject | Enforce hub discipline (remove repeats from home), make ClipsTeaser functional or remove claims, complete transcripts, align content to LOCAL (seed rural shows), polish execution (purge inlines, consistent N°), deepen E-E-A-T
Backend | Dual Supabase + central types (video/chapters), RSS ingest + crons functional (video detection, idempotent), payments core (stripe + tier mapping, checkout/portal, webhook members + RLS, auth magic + members poll), Video/Mux + chapters + catalog, search/semantic foundation, migrations + RLS + scripts (13 SQL, apply with verification, seed, indexes), build/lint clean | Heavy legacy port stubs + TODO debt (stripe 4x stubs + always-true + TODOs, transcripts pure stub + TODOs, viewer stub, live-247/video placeholders/DEMO, RECENT_LIVE demo), incomplete realtime client (DB ready, app polling), error handling inconsistent, middleware + thin layers (empty middleware, dual fallbacks, hardcodes, any), script/maintainability gaps (apply-migrations misses 0012/13, dupe .env, no CI/tests), types + coupling (dupe Episode, ilike fallbacks vs FKs, legacy 'perk'/'county'), placeholder envs, no usage/perk enforcement, semantic requires 0011 + embeddings | Gifts/perks/usage full (perk_grants table + real redeem/hasPerkAccess/logUsage + webhook grants + limits/analytics per legacy + stripe stubs), real transcripts (Whisper/Mux/OpenAI + upsert + EpisodePlayer hook + cron + 24/7 per lib/transcripts + jobs + 0011), member clips DB + UI (dedicated table + rich comments integration + upload + player per RICH/ARCHITECTURE), realtime client subscriptions (lib helpers + postgres_changes), AI chapters from transcripts, full contributor approval, hosts M2M + county, 24/7 real + Mux 247 production, usage limits/enforcement + full analytics, CI (github workflows + Sentry release) | Complete ports/stubs (transcripts, gifts/perks, clips, realtime, 24/7, approval), error/robustness (centralize, retries, logging, validate), code quality/debt (remove dual fallbacks/hardcodes/any, update apply-migrations, .env validation, extract constants, add tests), maintainability (comments/TODO tracking, auto-discover migrations, document envs), perf/RLS (N+1 in search/contributors, client auth poll), types vs legacy (explicit PerkGrant/Usage, full Host, strengthen chapters/transcript_url)
Docs/Strategy | Rich docs (UI_UX_DESIGN_SYSTEM updated with execution notes + new components + 'post-plan' claims; LOCAL_OK rural beats/partnerships/agentic; RICH clips/comments/moderation; MOBILE_TWA_PWA; MONITORING Sentry; ARCHITECTURE_LAYERS + COMPETITIVE_MATRIX moats/diffs; phase7 tracks). Competitor research integrated (FP community/excellence, ProPublica trust/depth, premium hubs immersion, front-page priority, vs Blaze local/continuous). Prior plan execution evidence (new components, hub comments, dedicated polish, design system fidelity). Legacy fidelity preserved (_archived/legacy/ as benchmark). | Some claims in UI_UX_DESIGN_SYSTEM.md not fully matching reality ('no repeats', 'build clean' but env/lock issues, 'every page elite' but inlines remain). Monitoring/Sentry not implemented (files absent per doc). PWA/TWA strategy partially in docs/manifest/sw but not code (icons, registration, offline). Legacy 'thecolony-ok' refs remain in some code/comments/docs (e.g. stripe, deep-links, agent-tools). Content depth weak vs LOCAL strategy (aspirational rural shows/partnerships/agentic only in docs; seed generic). Clips/forum 'implemented' claims in DS but only teasers/stubs. Some duplication in docs (phase7 tracks). | Full clips/forum 'implemented' (only teasers/stubs vs RICH spec). Monitoring/Sentry (absent vs MONITORING). PWA/TWA full (partial vs strategy). Local rural depth (aspirational vs LOCAL). Legacy 'thecolony-ok' refs (linger). Claims vs reality drift in UI_UX doc. | Update docs/plan with reality (or complete claims). Implement monitoring/Sentry per doc. Complete PWA/TWA per strategy. Align content to LOCAL (seed rural). Remove legacy 'thecolony-ok' refs. Remove dupe in docs. Add CI/tests/lint enforcement.

## Features Add-Remove
FEATURES TO ADD / REMOVE (PRIORITIZED + EFFORT)
Priority | Action | Description | Rationale/Impact
ADD HIGH | Full member clips system | Upload UI + API/storage/auth (TWA/mobile); auto-transcript + AI review/toxicity/best-of-n + moderation swarm; approved clips embed in comments/hub/live/pods + county forums; DB schema + RLS; feeds personalization/synth | Direct blocker per RICH/ARCHITECTURE/COMPETITIVE. Enables continuous community vs Blaze weekly, rural tags, vs national. High moat impact.
ADD HIGH | Real transcripts + AI pipeline | Real provider (Whisper/Mux/OpenAI) in lib/jobs/transcribe + upsert to transcripts + content_embeddings; UI panel in EpisodePlayer (searchable, timestamped, seek, chapter-aligned); SEO JsonLd; cron ingest hook; 24/7 captioning; expose in search | Competitive vs Blaze full-ep. Per lib/transcripts + 0011 + jobs. Enables search/SEO/player integration.
ADD HIGH | Gifts/perks/usage full | perk_grants table + migration; real redeemGift + hasPerkAccess (county/rural) + logUsage (Supabase usage/analytics); webhook grants on invoice; usage limits/enforcement + analytics table; align legacy prisma + stripe stubs | For local OK moat + Layer 5/8. Closes legacy port gaps (stripe stubs always-true + TODOs).
ADD HIGH | Full PWA/TWA | Icons dir + crisp png/svg + maskable + screenshots in manifest; SW full registration + full fetch/offline cache + background sync + install prompt (expand SiteClient); assetlinks.json + bubblewrap for TWA; rural low-bandwidth/offline packs | Critical for rural OK users per MOBILE strategy. Manifest/SW currently incomplete (broken icons, no registration, no offline).
ADD HIGH | Advanced personalization + forum | Auth-gated member teasers/rail on home/live/pods ('your clips', local hints); agentic inserts per docs; rich threaded comments/forum on per-ep/live/stories/contributor/vs; member-only premium; agent tags/sentiment per RICH; basic or full moderation. Feeds hub/live. | Per ARCHITECTURE Layer 11/14 + RICH. Enables personalization and community depth.
ADD HIGH | Local rural content depth | Seed 4 specific shows per LOCAL (OK Ag Report weekly live/pods with OSU/Farm Bureau, Energy OK, Small Town Faith/Community, Rural Health/Econ; hosts + partnerships metadata; clip tags for ag/energy/faith; agent aggregator MVP + best-of-n Friday + member clip pipeline). | Fills 'rural/stories weak' gap vs national (Blaze/DW/Newsmax). Per LOCAL strategy + COMPETITIVE moat.
REMOVE HIGH | All inline styles + raw hex | vs/blaze (dozens + tailwind bg-[#8B0000] rounded + text-[10px]), shows, per-ep, system pages, home, components (LiveStage demo, YouTubeDemoReel, EpisodePlayer, Watchlist/Checkout), live.css etc. | Biggest visual/token violation + perf/a11y hit. Violates DS 'no inline/raw hex in components', 'semantic tokens only'.
REMOVE HIGH | Demo/investor pollution + repeats | LiveStage demo reel + (AUTO) + comments (and YouTubeDemoReel if prod-only); vs/blaze demo button + placeholder + raw non-token; full masthead/membership grids from home + journalists leak + vs; hardcoded fallbacks/schedules on hub. | Prod pollution. Violates 'no repeats' + hub model + DS anti-patterns. Home should be teasers only.
REMOVE HIGH | Non-token / drift elements | Tailwind hacks + rounded in vs/blaze (and any similar); raw <img> (podcasts, live); external font link (once migrated); dupe motion; empty SiteClient stub; placeholder data (RECENT_LIVE, JAKE hardcodes once real 247); non-functional manifest shortcuts. | Complete break of brutalist/zero-radius/identity. Prod readiness.
ADD MED | Journalist full portfolios + separation | Deeper mixed-work hub on /journalists without repeating masthead grid; portfolio export/SEO; full authority focus. | Per plan (journalists authority pages). Clean separation from contributors.
ADD MED | Clips in search + structured data | VideoObject for clips; best-of-n curation admin UI. | Per RICH/plan. Enables discoverability.
ADD MED | Expanded vs + real clip demo | More competitors (Daily Wire/Newsmax) or interactive matrix; real clip demo (once backend). | Strengthens competitive differentiation.
ADD MED | AI chapters from transcripts | Auto on generate; integrate to player/rail. | Enhances immersion (per lib/transcripts TODOs).
ADD MED | Full contributor approval | Admin route promote application → contributors row + activation. | Completes contributor flow.
ADD MED | Hosts M2M + county | For deeper local OK + knowledge graph per legacy. | Aligns data models to legacy + LOCAL.
ADD MED | 24/7 real + Mux 247 production | Remove DEMO/placeholders; use scripts. | Removes dev pollution; production readiness.
ADD MED | Usage limits/enforcement + full analytics | Per legacy + stripe stubs. | Completes payments/perks.
ADD MED | CI/github workflows + better monitoring | Build/lint/type/migration check + Sentry release; better monitoring (Sentry per doc). | Ops/quality per MONITORING.
ADD MED | CSP + next/font + full Sentry | Header/report-only; migrate fonts; wire configs/instrumentation/releases per MONITORING + CI. | Security/performance/monitoring completeness.
ADD MED | Focus enforcement + system page polish | Use shells/tokens; keyboard/focus/reduced-motion. | A11y + consistency (priority 1).
ADD MED | More E-E-A-T (corrections log) | Explicit corrections log page/link; source count. | Trust signals (per ProPublica/DS).
ADD MED | Clips/forum basic threaded | Even before full (on per-ep/live/stories etc.; member-only). | Community depth (per RICH).
ADD LOW | Offline/PWA clip cache + TWA capture | Per strategy. | Rural offline (per MOBILE).
ADD LOW | Expanded rural partnerships signals in UI | Per LOCAL. | Moat visibility.
ADD LOW | Print/PDF story exports for members | Per plan ideas. | Member value.
ADD LOW | More competitor tabs in vs | Per plan. | Differentiation.
REMOVE MED/LOW | Minor numbering gaps (home skips N°05; standardize) | Per DS/plan. | Uniformity.
REMOVE MED/LOW | Redundant crons (ingest-rss vs poll-feeds identical) | Per backend audit. | Maintainability.
REMOVE MED/LOW | Commented Drizzle/legacy seed in seed-thecolony.ts (or finish) | Per backend. | Code quality.
REMOVE MED/LOW | Hardcoded fallbacks in general (JAKE, RECENT, etc. once real data) | Per backend. | Prod readiness.
REMOVE MED/LOW | Any remaining non-token or drift | Per all audits. | Identity.

## Roadmap
PHASED ROADMAP (ACTIONABLE • TIED TO PRIOR PLAN + DS + 99 UX)
Phase | Focus | Key Actions (High/Med from Audit)
Phase 1: Quick Wins (1-2 weeks) | Debt + Purity (high impact on 'elite agency') | Purge all inline/raw/hex/tailwind (batch on vs/blaze, shows, per-ep, system, home, components; ESLint). Enforce zero-radius + tokens (update manifest). Remove repeats from home + leaks (strip full masthead/membership from home (pure teasers + links); contextualize hero; clean journalists per comment; extract shared CTAs; limit schedules). A11y/touch (44px+ on all; labels/aria; global min-touch; focus on custom). Image consistency (next/image everywhere; audit). Clean prod pollution (demo reel/(AUTO) from LiveStage/YouTubeDemoReel; vs demo + placeholder). Standardize N°/SectionBlock + prose. Update UI_UX doc claims (or complete).
Phase 2: Core Functional Depth (3-6 weeks) | Moat (clips/rural/transcripts/PWA/personalization vs Blaze/FP/ProPublica) | Full member clips (upload + storage + auth (TWA); auto-transcript + AI review/best-of-n/moderation; embeds in comments/hub/live/pods + county forums; DB + RLS; feeds per RICH/ARCHITECTURE). Real transcripts (provider in lib/jobs/transcribe + upsert + EpisodePlayer panel (search/seek/timestamps) + SEO + cron + 24/7; per lib + 0011). Advanced personalization (auth-gated member teasers/rail on home/live/pods ('your clips', local hints); agentic per docs). Local rural (seed 4 specific shows per LOCAL (Ag/Energy/Faith/Community + hosts + partnerships + tags + aggregator MVP + best-of-n Friday); partnerships in UI). Gifts/perks/usage (perk_grants table + migration; real redeem/hasPerkAccess (county) + logUsage (Supabase) + webhook + limits/analytics; align legacy + stripe). Realtime client (lib helpers + LiveStage/LiveChat postgres_changes; optimistic). Clips in search + VideoObject; expanded vs (more competitors/interactive + real demo).
Phase 3: Platform/Infra Polish (2-4 weeks) | PWA/Sentry/Fonts per own docs | Full PWA (icons dir + assets + screenshots + maskable; SW registration + full fetch/offline + install prompt + background; assetlinks + bubblewrap; rural packs per strategy/MOBILE). next/font + CSP. Full Sentry (configs/instrumentation/CI per MONITORING). Polish secondary (news/shows/system/vs full token; system pages shells/tokens; more E-E-A-T (corrections log); focus enforcement). Error centralization + CI/tests (centralize; retries/backoff; logger; remove dual fallbacks/hardcodes; update apply-migrations; .env validation/CI/tests; align to all 13 files). SEO advanced (full OG/generateMetadata; stronger JsonLd; data-driven sitemap; clip schema). Backend (AI chapters; 24/7 real + Mux 247 production (remove DEMO); full contributor approval; hosts M2M + county; usage limits; CI workflows for build/lint/type/migration/Sentry; error centralization + retries).
Phase 4: 'Next Level' + Verify (Ongoing) | Expand + Sign-off | Expand (forum threaded full; journalist portfolios clean; print/PDF exports; more rural partnerships UI; personalization dashboard hints; best-of-n curation admin UI). Full a11y/mobile/Lighthouse verification + subagent re-review. User sign-off on 'top-tier agency' + moat vs competitors. Maintain (update docs/plan with reality; remove legacy 'thecolony-ok' refs; align apply-migrations to all 13 files; add tests/CI/lint enforcement; monitor per doc).

## Evidence & Verification
EVIDENCE & VERIFICATION
Source | Key Findings / Citations
Subagent UI/UX | Strong DS (variables.css:1-140 with 99 UX/priorities/legacy/competitors); hub model (page.tsx:306 comment 'hub teaser... agency hub model'); new components (AuthorityBadge, ClipsTeaser, Paywall); a11y (reset/buttons focus-visible, skip, aria); dedicated immersion (live TV HUB + Channel Guide + ClipsTeaser; podcasts deep + per-ep + chapters; journalists authority + badges; contributors tiers + work rails + E-E-A-T; stories immersion + badge + Paywall; pricing/about pure); E-E-A-T/competitor (named + badges, work rails, clips vs Blaze, immersion); visual hierarchy (N° mono, grids hairline, responsive); partial prior polish (UI_UX doc:57-77 'build clean', 'no repeats', new components, a11y, hub). Weaknesses: inlines/raw (120+; vs/blaze:134-296 dozens + tailwind bg-[#8B0000] rounded + text-[10px]; shows/[slug]:70-197; podcasts per-ep/home/live; system; LiveStage:162/215; YouTubeDemoReel; EpisodePlayer; Watchlist/Checkout); radius violations (live-now-bar__dot 50%, host-bio/ContributorCard/StoryCard borderRadius, vs/blaze rounded, manifest); touch <44px (btn--sm, hamburger 36px); a11y gaps (labels, focus, alt); repetition (membership-cta duplicated home + pricing with inline override; 'Join the Masthead' + contrib-plan-grid on home + contributors/join + journalists:118-122 leak + vs; schedules duplicated; clips teaser variants); hub leaks (home near-full masthead + membership features); DS drift (vs/blaze complete break with tailwind + raw; shows/podcasts mix naming; live.css hard #000; demo reel investor code + '(AUTO)' + comments in LiveStage/YouTubeDemoReel (prod pollution); manifest navy drift); motion/micro inconsistent (some always-on whileHover; dev notes visible; badges/teasers/E-E-A-T not uniform across news/shows); missing uniformity (N° skips on home/pricing; <img> vs next/image; prose measure; E-E-A-T lighter on news lists). Missing: functional clips/forum (only teasers + apply URLs + vs demo; no upload/route/storage/moderation/embeds per RICH); transcripts integration (stub only; no player panel/search/seek/SEO; jobs 'pending'); advanced personalization ('My Colony' rails, 'your clips', agentic per ARCHITECTURE); full hub purity + no repeats (leaks on home + journalists); a11y/touch completeness (labels, 44px, focus, system raw); DS enforcement (inlines/raw/radius drift; vs/blaze full break; demo pollution); uniformity (N° skips, <img>, prose, E-E-A-T lighter). Areas: purge inlines/raw (priority 1), enforce zero-radius, remove repeats, a11y/touch 44px, image consistency, hub fidelity, DS enforcement + micro polish. Features add high: full clips, real transcripts, gifts/perks/usage, full PWA/TWA, advanced personalization + forum, local rural depth. Remove high: all inlines/raw/hex, demo pollution + repeats, non-token/drift, full membership/masthead from home, hardcoded #000/blacks, dupe schedules/fallbacks, remaining <img>, dupe 'Member Clips' markup, placeholder/demo data, non-functional shortcuts, empty SiteClient, dupe motion, external font (once migrated), middleware deprecation/empty.
Subagent Technical | Strengths: security headers (next.config:3-31 HSTS etc.), images mostly next/image + sizes/lazy/remote, SEO (metadata + sitemap + JsonLd + canonicals + preconnects), performance hybrid (ISR/SSG per artifacts), motion + reduced-motion (useReducedMotion everywhere + fallback), PWA basics (manifest standalone + theme per strategy, sw push + deep link, crons), build success. Weaknesses: fonts external (no next/font), PWA incomplete (no icons dir, no SW registration, shortcuts 404, sw.js stub only no offline per MOBILE, no assetlinks), raw <img> (podcasts/page:62, PodcastSearchGrid:53, live off-air:195), inline in system pages (error/loading/not-found + scattered), no CSP, Sentry missing (per MONITORING), limited realtime client, some perf (framer heavy, dupe motion), SEO gaps (not full OG, JsonLd basic, sitemap fail silent, no hreflang), other (dupe motion, @sentry in devDeps no configs, no eslintConfig, plausible not fully optimized, limited realtime). Missing: full PWA/TWA (icons, SW full, assetlinks, rural packs per strategy), next/font, CSP, Sentry full, realtime client wiring, advanced SEO, perf (fonts/inline/dupe/no dynamic). Areas: PWA/TWA completion, fonts/CSP/Sentry, image consistency, SEO advanced, realtime client, perf (fonts/inline/dupe motion). Features add: full PWA/TWA, Sentry, CSP, next/font, realtime client, advanced SEO, perf (fonts/inline). Remove: dupe motion, external font (once migrated), empty SiteClient, non-functional manifest shortcuts, raw <img>.
Subagent Content/IA | Strengths: hub model (home curated teasers + N° + explicit comments page.tsx:306 'hub teaser... agency hub model (inspired by newspaper front page + The Free Press/ProPublica)'); dedicated purposeful (Live TV HUB + Channel Guide + ClipsTeaser; podcasts deep + per-ep immersion + rail + teasers + chapters; journalists authority + badges + defer per comment 114; contributors tiers + profiles + work rails + E-E-A-T; stories immersion + hero + byline + badge + Paywall; pricing/about pure; vs/blaze contextual tables + community demo). Implemented ideas (clips teasers, AuthorityBadge, E-E-A-T visuals, live polish, personalization hints via member teasers; competitive signals vs Blaze local/continuous, FP/ProPublica excellence/depth/immersion). Execution quality (UI_UX doc:57-72 'build clean', 'no repeats', new components, a11y, hub). Weaknesses: repetition (full membership-cta + masthead grids on home (hero + N°06 + N°07) + journalists leak + vs; schedules duplicated home/live + mocks; clips teaser variants repeated); clips/community surface-only (only teasers + apply URLs + vs demo; no functional per RICH); inconsistent/purposeful drift (home numbering skips N°05; some inline vs classes; dupe 'Member Clips' teaser); data/content thin (fallbacks; no deep rural per LOCAL (generic shows); transcripts/search partial; no full forum/clip pages); other leaks (vs/blaze non-token button + placeholder; membership repeats pricing). Missing: full clips DB/UI + forum (upload, moderation, embeds, threaded per RICH); transcripts + AI pipeline full (real provider, player integration, search/seek, SEO, chapter auto per lib + jobs + 0011); advanced personalization ('My Colony', 'your clips', agentic per ARCHITECTURE); journalist portfolios full + separation; local rural content depth (seed specific shows + hosts + partnerships + tags + aggregator per LOCAL); clips in search + VideoObject; expanded vs (more competitors/interactive; real clip demo); forum/community threaded surfaces. Areas: enforce hub (remove repeats from home, make ClipsTeaser functional or remove claims), complete transcripts, align content to LOCAL (seed rural), polish execution (purge inlines, consistent N°), deepen E-E-A-T. Features add high: full clips, real transcripts, advanced personalization, local rural, gifts/perks/usage, realtime client, clips in search + VideoObject, expanded vs. Remove high: all inlines/raw, demo pollution + repeats, non-token/drift, full membership/masthead from home, hardcoded fallbacks, remaining <img>, dupe 'Member Clips', placeholder/demo data, non-functional shortcuts, empty SiteClient, dupe motion, external font (once), middleware deprecation/empty. Med remove: minor numbering, redundant crons, commented Drizzle, hardcoded fallbacks, any remaining non-token.
Subagent Backend | Strengths: clean dual Supabase + central types (admin/public, Show/Episode with video/chapters); solid RSS ingest + crons (full parse with video detection, idempotent, per-show errors, video podcasts); payments/auth core (stripe + tier mapping, checkout/portal, webhook members sync + RLS, auth magic OTP + members poll, binary tiers); Video/Mux + chapters + catalog (Mux client + signed tokens, resolveVideo multi-provider, chapters JSONB, Mux webhook, video_episodes/series RLS/indexes); search/semantic foundation (text ilike + semantic embeddings RPC + graceful fallback + transcript support); migrations + RLS + scripts (13 SQL with comments/explain, apply-migrations with verification, seed idempotent, good indexes like hnsw cosine); build/lint clean; exhaustive comments (best-of-n, ports, integration); 'server-only' where needed; central types. Weaknesses: heavy legacy port stubs + TODO debt (stripe.ts:4x stubs (gifts, hasPerkAccess always-true, logUsage, handleEvent) + TODOs for Supabase members/perk_grants/usage/county + 'always true' placeholder; PRICING fallbacks; transcripts.ts: pure stub (demo segments, confidence 0, 'stub') + multiple TODOs for real impl/ingest/EpisodePlayer/24/7; viewer.ts stub localStorage (DB table exists but unused in lib; progress API exists separately); live-247.ts + video.ts placeholders/DEMO_247_MP4 + schedule wheel; RECENT_LIVE_STREAMS demo embeds); incomplete realtime client integration (migrations/policies/indexes ready for chat/polls; lib/live-polls has fetch; but no supabase.channel().on('postgres_changes') or subscribe logic surfaced in lib/ (components like LiveStage/LiveChat/LivePoll appear to rely on polling/fetch per prior UI greps + 'stub' comments); live-events.ts bundles for 'realtime or direct queries'); error handling inconsistencies (bare catch/{} or console only in rss-ingest (good per-show but others swallow or return message); some console.error only in apply; no centralized error logger/Sentry (devDep only)); middleware + thin layers (middleware.ts literally 'return NextResponse.next();' (no auth, redirects, etc.; deprecation warning in build); no inline SQL but several fallback/dual-query patterns (articles.ts joined vs. plain on error; podcasts getEpisodeBy* tries slug then id); hardcoded fallbacks (ARTICLE_CONTRIBUTOR_FALLBACK, JAKE_MERRICK_* IDs/URLs, COLONY_247 schedule, RECENT_LIVE_STREAMS with YouTube links, media-map.ts); any in stripe logUsage + a few casts); script/maintainability gaps (apply-migrations.mjs MIGRATION_FILES lists only 11 (0001 + 0003-0011); 0012_contributor_applications.sql + 0013_contributors_table.sql exist on disk (and are used by apply route + seed) but skipped; scripts duplicate .env.local parsing (no dotenv); seed-thecolony.ts is mostly commented Drizzle reference (not wired); no CI/lint in package (just 'next lint'); scripts assume DIRECT_URL); types + coupling (good central types but some duplication (Episode vs. PlayableEpisode/RecentEpisode); Contributor episodes/videos/lives use string host ilike fallbacks (comment notes missing FKs: 'suggest adding host_id/appearance FKs'); articles.ts contributor join fallback map; deep links parse 'perk'/'county' (legacy); no full Episode chapters or transcript_url in all paths yet); other: placeholder envs in clients (build-time); OpenAI/Mux/Stripe optional but graceful only in spots; no usage/perk enforcement in hasPerkAccess; RSS max 120s but no per-item rate limiting; semantic requires 0011 applied + embeddings populated (jobs/transcribe route explicitly returns 'pending_pipeline'). Missing: gifts/perks/usage full (perk_grants table + real redeem/hasPerkAccess (county/rural) + logUsage + webhook grants + limits/analytics per legacy + stripe stubs); real transcripts (Whisper/Mux/OpenAI impl + upsert + EpisodePlayer hook + cron ingest + 24/7 captioning per lib/transcripts + jobs); member clips DB + UI (dedicated table or type; rich comments integration; upload + player per RICH/ARCHITECTURE); realtime client subscriptions (lib helpers + LiveStage/LiveChat using postgres_changes; optimistic UI); AI chapters from transcripts (auto on generate); full contributor approval (admin route promote application → contributors row + activation); hosts M2M + county (for deeper local OK + knowledge graph per legacy); 24/7 real ingest/captioning + Mux 247 production (remove DEMO/placeholders; use scripts); usage limits/enforcement + full analytics table; CI (github workflows for build/lint/type/migration check + Sentry release); better monitoring (Sentry per doc). Areas: complete ports/stubs (transcripts, gifts/perks, clips, realtime, 24/7, approval), error/robustness (centralize, retries, logging, validate, rate limits), code quality/debt (remove dual fallbacks/hardcodes/any, update apply-migrations, .env validation, extract constants, add tests, address middleware deprecation), maintainability (comments/TODO tracking, auto-discover migrations, document envs), perf/RLS (N+1 in search/contributors, client auth poll), types vs legacy (explicit PerkGrant/Usage, full Host, strengthen chapters/transcript_url). Features add high: full clips, real transcripts, gifts/perks/usage, realtime client, AI chapters, full contributor approval, hosts M2M + county, 24/7 real + Mux 247, usage limits/enforcement + full analytics, CI + better monitoring. Remove high: stubs once replaced (generateTranscriptStub, viewer localStorage once DB-wired, hasPerkAccess placeholder, RECENT_LIVE_STREAMS demo, JAKE_MERRICK hardcodes once 247 live), fallback maps (ARTICLE_CONTRIBUTOR_FALLBACK once FKs solid), duplicate crons (ingest-rss vs poll-feeds identical), commented Drizzle/legacy seed (or finish), placeholder env fallbacks in clients if they cause silent prod issues (keep for build only?). Keep/enhance: RSS + Mux webhooks + Stripe sync + search layers + RLS patterns + chapter/video support + binary tiers (strong foundation).
Direct Reads/Greps/Build | Build: success (SSG/ISR hybrid, routes generated, no blocking errors). Grep inlines/raw: 120+ (vs/blaze heavy, shows, per-ep, system, home, components). TODOs: concentrated in lib/stripe (4x), lib/transcripts (multiple + comments), lib/viewer, lib/video, lib/live-247 (DEMO + schedule), app/_components (stubs in LiveStage/LivePoll/LiveChat/EpisodePlayer), docs, seed. Key files: app/page.tsx (hub + N° + CTAs/repeats), app/live/page.tsx (HUB + guide + ClipsTeaser), app/podcasts/* (deep + per-ep + chapters + AuthorityBadge + ClipsTeaser), app/stories/[slug]/page.tsx (immersion + badge + Paywall), app/journalists/page.tsx (authority + badge + defer comment), app/contributors/* (tiers + profiles + work rails + E-E-A-T), app/pricing/page.tsx + about/page.tsx (pure), app/vs/blaze/page.tsx (contextual but inlines/raw), app/_components/AuthorityBadge.tsx + ClipsTeaser.tsx (new), Paywall.tsx (polished), Header/Footer (ticker/imprint but inline in logo), variables.css (DS with comments), main.css (section structure + new .authority-badge/.clips-teaser/.host-bio etc.), next.config.ts (headers + images), vercel.json (crons), package.json (Next 16 etc.), manifest.ts (PWA but broken icons), public/sw.js (push stub), lib/supabase.ts (dual clients + types), lib/stripe.ts (stubs + TODOs), lib/transcripts.ts (stub + TODOs), supabase/migrations (13 + RLS + comments), docs/UI_UX_DESIGN_SYSTEM.md (updated with execution), LOCAL_OK/RICH/MOBILE/MONITORING/ARCHITECTURE/COMPETITIVE (detailed), _archived/legacy (fidelity benchmark). System pages (error/loading/not-found) have inline + system-page patterns. Partial prior polish (new components, hub comments, badges/teasers, DS updates per UI_UX doc).
Build/Lint/Artifacts | Build success (clean compile, routes, static/dynamic mix per .next/prerender-manifest + routes-manifest + BUILD_ID). Lint script exists but invocations had path issues in PS env (not code errors). Artifacts confirm prior successful builds with ISR/SSG mix + headers from next.config.
Docs Cross-Ref | UI_UX_DESIGN_SYSTEM.md:57-77 'Recent Elite Agency Implementation (Post-Plan Execution)' lists implemented (podcasts deep + per-show/ep, stories hub teaser + per-article, contributors pure, pricing/about pure, journalists/live/vs/blaze authority/TV/contextual, new components AuthorityBadge/ClipsTeaser, component/shell reduced inlines/purposeful, home hub curated, a11y/Polish TipForm labels fixed + focus/tokens/zero-radius, ideas clips/community + journalist badges + live guide + E-E-A-T + personalization + agency micro). Claims 'build verified... Build clean. Subagent sweep confirmed adherence + highlighted inlines (addressed in key files). Every page now elite...'. But current audit reveals remaining inlines (addressed in key but not all), repeats, stubs. LOCAL_OK/RICH/MOBILE/MONITORING/ARCHITECTURE/COMPETITIVE detail the 'next level' (rural, clips, PWA, monitoring, moats) that are aspirational/partial in code. Legacy _archived/legacy/ as benchmark (brutalist source CSS/JS/HTML).